## 30-Day Calendar
WheelTodo — 30-Day Beta-Launch Content Calendar
Day 1 = first Monday of the push (set real dates in your tool). 26 posting days + 4 on-brand rest days. Cross-post all reels to TikTok / IG Reels / YouTube Shorts. Caption the verbal hook (most watch muted).
Day | Weekday | Phase | Platform | Pillar | Format | Concept / Working title | Visual hook (0-1s) | Verbal hook | Text overlay | CTA | Asset needed | Status
1 | Mon | Pre-launch | TT · IG Reels · Shorts | Relatable pain | Talking head | '23 tasks, 0 done' — name the freeze | Overflowing list, phone face-down, staring at ceiling | I wasn't lazy. I was paralyzed. | 23 tasks. 0 done. there's a reason. | Follow — the fix drops this week | TH clip + list mockup | Planned
2 | Tue | Pre-launch | TT · IG Reels · Shorts | Niche · ADHD | POV / text | 'Your brain has 40 tabs open' | Frantic tab-switching metaphor | ADHD brains can't pick a starting point. | why 'just start' never works for us | Comment if this is you | Screen-rec + TH | Planned
3 | Wed | Pre-launch | TT · IG Reels · Shorts | Oddly satisfying | Teaser b-roll | First peek at the wheel (no name reveal) | Full-screen wheel mid-spin, crisp tick, lands on one | (whispered) just pick one for me… | what if you never had to choose again 👀 | Waitlist link in bio | Spin screen-rec | Planned
4 | Thu | Pre-launch | TT · IG Reels · Shorts | Relatable pain | Skit | The procrastination spiral | 'Getting ready to be productive' — watering plant, tidying desk | Me 'about to start' for the 4th time today | POV: you've 'started' 6 times today | Follow for the actual fix | Skit | Planned
5 | Fri | Pre-launch | TT · IG Reels · Shorts | Trend-jack | Green-screen | React to 'just make a list' advice | Green-screen over a productivity influencer | The list IS the problem — I can't pick. | telling an overwhelmed person to 'make a list' 💀 | Real fix drops Monday | Green-screen edit | Planned
6 | Sat | Pre-launch | TT · IG Reels · Shorts | Oddly satisfying | ASMR | Spin compilation (loopable) | 3–4 spins back-to-back, tick + land | (none / whispered) | the most satisfying way to start a task | Name drops next week 👀 | Spin compilation | Planned
7 | Sun | Pre-launch | Story / static only | Rest day (on-brand) | Story only | We rest. So does our app. 🌿 | Calm static — streak flame staying lit on a rest day | — | we take rest days. soon you'll see why that matters. | — | Static Rest Mode card | Planned
8 | Mon | LAUNCH WEEK | TT · IG Reels · Shorts | Relatable pain | Hero reveal | THE reveal — core loop | Dump list → spin → lands → instantly flips to a RUNNING Pomodoro | Stop choosing. Spin — the timer's already counting. | meet WheelTodo · 23 tasks · one spin · now you're already doing it | Beta's live — link in bio | Hero screen-rec | Planned
9 | Tue | LAUNCH WEEK | TT · IG Reels · Shorts | Differentiator: kind+rest | Emotional | 'Rest counts too' | Collapse on couch, wrecked; phone shows streak flame STAYING lit | I took a nap and my to-do app… congratulated me. | the productivity app that rewards you for resting | Join the beta | Couch clip + streak UI | Planned
10 | Wed | LAUNCH WEEK | TT · IG Reels · Shorts | Niche · ADHD | Feature demo | The energy check-in | App asks 'How's your energy?' → taps Drained → suggests gentle wins | It asks how I feel before it asks what I'll do. | a to-do app that checks on you first | Beta link in bio | Check-in screen-rec | Planned
11 | Thu | LAUNCH WEEK | TT · IG Reels · Shorts | Proof & momentum | Vlog | 'I let a wheel run my whole day' — Day 1 · SERIES | Morning: 'the wheel decides everything today' | For 24h I'm not allowed to choose a single task. | I let an app control my entire day | Follow for Day 2 | Day-in-life montage | Planned
12 | Fri | LAUNCH WEEK | TT · IG Reels · Shorts | Oddly satisfying | ASMR · sound-on | Spin + tick + completion confetti | Spin → tick → lands → confetti on complete | (none) | turn your sound on 🔊 | Beta link in bio | Spin+confetti (gen-audio SFX) | Planned
13 | Sat | LAUNCH WEEK | TT · IG Reels · Shorts | Proof & momentum | Testimonial | First beta-tester reactions | Screenshot carousel of DMs / reactions | — | what beta testers are saying after 3 days | Join them | Screenshot reel | Planned
14 | Sun | LAUNCH WEEK | Story / static only | Rest day (on-brand) | Story only | Sunday = rest day, streak safe | Calm static | — | Sunday. your streak's safe. 🌿 | — | Static card | Planned
15 | Mon | Use-cases | TT · IG Reels · Shorts | Niche · students | Study-with-me | 'The app picks what to study' | Desk study clip, spin selects the subject | study with me — but it makes the decision | study with me (the app picks) | Beta link in bio | Desk study clip | Planned
16 | Tue | Use-cases | TT · IG Reels · Shorts | Niche · couples · FRANCHISE | Skit | 'Who does the dishes?' | Two people glaring at a full sink, phone between them | We argue about chores daily. Not anymore. | we let the wheel decide who does the dishes | Tag your roommate | Skit | Planned
17 | Wed | Use-cases | TT · IG Reels · Shorts | Differentiator: kind+rest | Educational | 'Streaks shouldn't punish rest' | Explainer: rest protects the streak | Every streak app breaks if you rest. Ours doesn't. | rest days keep your streak alive | Join the beta | UI explainer | Planned
18 | Thu | Use-cases | TT · IG Reels · Shorts | Proof & momentum | Vlog | Wheel-runs-my-day — Day 2 / payoff · SERIES | Results montage | Most productive day in weeks? | I let a wheel run my day — here's what happened | Follow | Montage | Planned
19 | Fri | Use-cases | TT · IG Reels · Shorts | Trend-jack | 'Apps that replaced X' | 'Deleted 3 to-do apps for this' | Dramatically deleting Notion / Reminders / sticky notes | I never DID the to-dos. This one makes me. | the to-do app that actually makes you do it | Beta link in bio | Phone screen | Planned
20 | Sat | Use-cases | TT · IG Reels · Shorts | Niche · overwhelm | Relatable | 'When everything needs doing and you freeze' | Quiet overwhelm, too many sticky notes | you're not lazy — you're overloaded | when everything's urgent and you freeze | Beta link in bio | Talking head | Planned
21 | Sun | Use-cases | Story / static only | Rest day (on-brand) | Story only | Community poll | Static poll sticker | — | what's your Sunday rest activity? 🌿 | Reply to vote | Poll story | Planned
22 | Mon | Retention | TT · IG Reels · Shorts | Oddly satisfying | ASMR | Theme aesthetics (4 themes) | Theme switch screen-rec, incl. dark | (none) | pick your vibe 🎨 (dark mode included) | Beta link in bio | Theme switch rec | Planned
23 | Tue | Retention | TT · IG Reels · Shorts | Differentiator: kind+rest | Values | Accessible high-contrast themes | A11y theme demo side-by-side | built for every brain — and every pair of eyes | accessible by default, not as an afterthought | Beta link in bio | A11y demo | Planned
24 | Wed | Retention | TT · IG Reels · Shorts | Niche · ADHD | Educational | 'Task initiation is the hard part' | Talking head + UI | The hardest part of any task is choosing it. So we deleted choosing. | task paralysis, solved | Join the beta | TH + UI | Planned
25 | Thu | Retention | TT · IG Reels · Shorts | Proof & momentum | Duet/stitch prompt | 'Show me your wheel' challenge | Prompt clip inviting stitches | — | stitch this with your task wheel | Use #WheelTodo | Prompt clip | Planned
26 | Fri | Retention | TT · IG Reels · Shorts | Trend-jack | Trending audio | 'Living in my head rent-free' | Meme edit: 17 unstarted tasks → one spin | (trending audio) | my 17 unstarted tasks vs. one spin | Beta link in bio | Meme edit | Planned
27 | Sat | Retention | TT · IG Reels · Shorts | Differentiator: kind+rest | Streak flex | '14-day streak — rested 4 of them' | Shareable streak card | guilt-free productivity is real | 14-day streak (and I rested 4 days) | Beta link in bio | Streak share card | Planned
28 | Sun | Retention | Story / static only | Rest day (on-brand) | Story only | Week recap | Calm recap static | — | another week, streak intact. 🌿 | — | Recap story | Planned
29 | Mon | Retention | TT · IG Reels · Shorts | Proof & momentum | Montage | '3 weeks of beta — what changed' | Before/after montage | from 23-tasks-frozen to actually done | 3 weeks in: what changed | Join the beta | Before/after montage | Planned
30 | Tue | Retention | TT · IG Reels · Shorts | Proof & momentum | Teaser | Body-double companion (ROADMAP — not yet shipped) | Cozy lofi room loop preview (mark as 'soon') | a little companion that sits with you while you work… | your focus, but make it lofi 🌧️ (soon) | Join beta to get it first | body-double loop (repo asset · unreleased) | Planned

## Pillars
Content Pillars (repeatable, not 10 one-offs)
Pillar | Why it works | Target mix | Core message | Best formats
Relatable pain | Widest top-of-funnel reach — decision paralysis / overwhelm is instantly recognisable. Front-loaded pre-launch. | 3 / 26 | You're not lazy, you're frozen — and that's fixable | Talking head, skit, POV text
Differentiator: kind+rest | The ownable wedge no competitor holds — rest protects your streak + an accessible, kind brand. Emotional + shareable. | 4 / 26 | Rest counts. Guilt-free, built for every brain. | Emotional, educational, UI demo, values
Oddly satisfying | Dopamine bait — the spin/tick loops; high watch-time + replays | 4 / 26 | The spin is the payoff | ASMR, loopable b-roll, streak flex
Niche use-cases | High save/share — ADHD, students, couples, parents | 6 / 26 | Made for your specific brain / situation | Feature demo, skit, study-with-me
Trend-jack | Rides reach of existing trends, formats & audio | 3 / 26 | We belong in this conversation | Green-screen, 'apps that replaced X', trending audio
Proof & momentum | Credibility + community — testimonials, the wheel-runs-my-day series, UGC, roadmap teases. Back-loaded as the beta matures and proof accumulates. | 6 / 26 | Real people, real momentum — and what's next | Testimonial, vlog/series, UGC prompt, teaser
Shape over time matters more than the raw mix: days 1–10 skew pain + satisfying (reach), days 11–30 add proof + niche (save/share + conversion). Plus 4 on-brand rest days = no reel, story only.

## Hook Bank
Hook Bank — mix & match across any reel (first 1s is everything)
Visual hooks (frame 0–1s) | Verbal hooks (first line) | Text-overlay hooks (burned-in)
Full-screen wheel frozen mid-spin | I wasn't lazy — I was paralyzed. | 23 tasks. 0 done. here's the fix →
Overflowing chaotic list, phone face-down | I let an app decide my entire day. | POV: you've 'started' 6 times today
You frozen, blank 'deer-in-headlights' stare | If your brain has 40 tabs open, watch this. | don't choose your task. spin it.
Satisfying tick as wheel lands on one task | The hardest part of any task is choosing it. So we deleted choosing. | the to-do app that actually makes you do it
Spin → screen instantly flips to a running timer | I took a nap and my to-do app congratulated me. | the productivity app that rewards you for resting
Collapse on couch; streak flame stays lit | Stop choosing. Spin — the timer's already counting. | a to-do app that checks on you first
Before/after: 23 unchecked boxes → 1 checked | Every streak app breaks if you rest. Ours doesn't. | rest days keep your streak alive
Energy check-in: tap 'Drained' → gentle tasks appear | It asks how I feel before it asks what I'll do. | the most satisfying way to start working

## Cadence & Channels
Cadence, Channels & Production Notes
Lever | Setting | Why / note
Rhythm | 6 posts/week + 1 on-brand rest day | Posting on rest days would contradict the brand. Sun = story/poll only.
Primary platform | TikTok | Highest organic reach for cold consumer apps; lead here, cross-post everywhere.
Cross-post | IG Reels + YouTube Shorts | Same master edit; use Adobe-style resize per aspect ratio (9:16 master).
Best post times | 12–1pm & 7–9pm local | Lunch + evening doom-scroll windows; test and let data move them.
Master format | 9:16, 7–15s, hard cut in <1s | No logo intro, no slow build. Hook frame must be loud on frame 1.
Captions | Always burned-in | Most watch muted — verbal hook ≈ the text overlay.
Loop | Make the spin loop seamlessly | Boosts watch-time & replays — the algorithm's favourite signal.
CTA | One soft CTA | 'link in bio' or 'comment WHEEL'. Never hard-sell.
Series to milk | #11/#18 (wheel-runs-my-day), #16 (couples chores) | Franchises > singles. Number the episodes.
Sound | Wheel tick + completion chime | gen-audio asset (also fills the app's unimplemented wheelSoundEnabled).
Roadmap gate | Body-double = 'soon', never 'now' | Not wired into the app yet — tease only (Day 30).

## Summary
Mix Check (auto-counts from the calendar)
Posts by pillar
Relatable pain
Differentiator: kind+rest
Oddly satisfying
Niche
Trend-jack
Proof & momentum
Rest day (on-brand)
Total rows
Posts by phase
Pre-launch
LAUNCH WEEK
Use-cases
Retention
Posting vs rest
Posting days
Rest days